## Items
Section | Item | Status | Implementation notes | Commit / files
Look & Feel | Home page — Add high-quality CPC logo (Saad to get) | Deferred | Placeholder cpc-logo.png still in place; awaiting hi-res asset from Saad. Logo plumbing already in place at both desktop/src/features/HomePage.tsx and desktop/src/features/AppShell.tsx (sidebar footer). | —
Look & Feel | Home page — Italic tagline: 'A Decision Support System to Optimize Manpower Sourcing' | Done | Tagline rendered under the title in italic, lighter color so it reads as supporting copy. | commit 1 / HomePage.tsx + styles.css
Look & Feel | Home page — Make the 3 icons larger | Done | SVG icons 34px → 52px, surrounding tiles 112px → 144px tall, label font 13px → 15px. | commit 1 / styles.css
Look & Feel | BU Selection — Tab to be added depending on discussion | Deferred (discussion) | Net-new workflow stage. Open questions: position in flow (before or after upload?), backend support, multi-tenant data persistence per BU. | follow-up PR
Look & Feel | Data Upload — Delete 'Workforce Studio' text; CPC logo at bottom of left panel | Done | Removed Workforce Studio label and alt text. Logo moved from sidebar header to sidebar footer (above engine status). | commit 1 + commit 6 / AppShell.tsx + styles.css
Look & Feel | Data Upload — Remove 'Upload workbook' from left-panel bottom | Done | Button label shortened: 'Upload workbook' / 'Upload new workbook' → 'Upload' / 'Upload new'. | commit 1 / AppShell.tsx
Look & Feel | Data Upload — After upload, single 'Data Loaded' message (not duplicate 'workbook loaded') | Done | Section eyebrow renamed to 'Data Loaded'. Subtitle row replaced with the loaded workbook filename so the header is informative without duplication. | commit 2 / UploadWorkspace.tsx
Look & Feel | Data Upload — Rename 'Subcontracted' → 'Outsourced' | Done | UI label updated on the metric card. NOT changed: the Excel SHEET NAME 'Subcontractor' (user file format requirement) and internal API field names (would break client compatibility). | commit 2 / UploadWorkspace.tsx
Look & Feel | Data Upload — Reorganize boxes (total full width on top, then in-house / outsourced / job families row) | Done | New data-health-total class for the full-width total card; data-health-grid--triple for the 3-card row below. | commit 2 / UploadWorkspace.tsx + styles.css
Look & Feel | Additional Inputs — No need for 'Brand new' on this sheet | Done | All 'brand-new family' wording stripped from button labels, wizard titles, and metadata rows. | commit 3 / MappingResolveWorkspace.tsx
Look & Feel | Additional Inputs — Add 'Job' to all 'families' (Add a Job Family, Name of job family, etc.) | Done | Custom families → Custom job families. Family name → Name of job family. Edit family → Edit job family. Define family from selected → Define job family from selected. | commit 3 / MappingResolveWorkspace.tsx
Look & Feel | Additional Inputs — '1 Custom' badge persistence across app restarts? | Answered (info) | Desktop React ALREADY persists custom families across restarts via localStorage (see App.tsx persistGet/persistSet on 'custom_families'). Streamlit is session-only — Streamlit was out of scope for this PR so no change there. | —
Look & Feel | User Assumption — No workbook/data-loaded window on top | Done | Upload metrics card no longer renders on the Ready (User Assumptions) stage; UploadWorkspace is now upload-stage-only. | commit 2 / App.tsx
Look & Feel | User Assumption — Drop repeated 'User assumptions'; just 'Optimization Mode' with two radio options | Done | In-content 'User Assumptions' eyebrow removed; the topbar's 'USER ASSUMPTIONS' green tab title remains as the single source of truth. Two-mode toggle preserved. | commit 4 / ScenarioControls.tsx
Look & Feel | User Assumption — If Target plan selected, show Target Manpower Plan window | Done | Already conditional (isTargetMode). Verified after the User Assumptions header cleanup. Auto-opens the target accordion when the mode toggles. | no change needed
Look & Feel | All Tabs — Remove second row in upper white strip; keep title in green, larger | Done | Topbar collapses to a single row. Green eyebrow promoted to a 22px display-font heading; subtitle row removed. Same treatment across Data Upload / Additional Inputs / User Assumptions / Output. | commit 1 / AppShell.tsx + styles.css
Structural | After homepage — list of companies with 'to be configured', click MGIC; tab 'BU Selection' | Deferred (discussion) | Same as the Look & Feel BU Selection entry — net-new stage that needs a design pass. Risk noted: tool currently assumes one BU per laptop. | follow-up PR
Structural | Reduce processing time after upload | Done | 94.06s → 19.25s on Manpower.xlsx (~4.9× faster). Root cause: normalize_lookup_text called 16.3M times and per-row dict rebuilds in get_numeric_from_row. Fix: lru_cache + hoist the per-DataFrame column resolver. Cache hit rate 99.94%. All tests still pass. | commit 7 / manpower_app/utils.py
Structural | After XLS processing — why is 'add a job family' visible? (discuss) | Done (resolved by hiding outside Target mode) | Button now only appears when 'Input and Optimize a Target Manpower Plan' is selected, with a short hint explaining the flow. In Current mode it's hidden — a family with no payroll rows has nothing to optimize. | commit 6 / MappingResolveWorkspace.tsx + App.tsx
Structural | Make Outsourceable / Fully Inhouse / Partially Outsourceable dynamic | Deferred (discussion) | Currently hardcoded in manpower_app/rules.py (OUTSOURCEABILITY_RULES dict). Open question: source for dynamic values — workbook column, in-app editor, or both? Affects rules, costs, optimization constraints. Backend rework required. | follow-up PR
Structural | Tool should handle Saudis-cheaper-than-non-Saudis (auto-correct) | Done | Saudi cost premium floored at 1.0× in three places (defense in depth): desktop slider min, manpower_api Pydantic validator, and manpower_app.costs.calculate_inhouse_cost_split. Saudis can no longer be configured as cheaper than non-Saudis from any code path. | commit 4 / costs.py + ScenarioControls.tsx + app.py
Structural | Hard inputs — edit ratio AND driver name (e.g., quarries labor vs quarries skilled labor) | Deferred (discussion) | Driver mappings are hardcoded in manpower_app/ratios.py:calculate_driver_values. Making this user-editable needs the same backend pattern as the dynamic-outsourceability item: new settings field, new API contract, propagation through the LP. Best done with #20. | follow-up PR
Structural | Target plan — ask about drivers so ratios can be recalculated | Deferred (discussion) | Depends on the editable-driver work (#22). Once a user can pin which profession is the ratio driver, the target plan UI needs an input for the driver headcount. | follow-up PR
Debugging | Risk input slider — should reach zero | Done | Slider min lowered from 0.01 to 0 in both UI (ScenarioControls.tsx) and API (Pydantic gt=0 → ge=0). At R=0 the LP constraint degenerates cleanly to O+I ≥ M; the rearranged closed-form (T−M)/R is only consulted when R>0. README updated. | commit 4 / ScenarioControls.tsx + app.py + README.md
Debugging | All tabs — '0' doesn't get deleted in number inputs | Done | Replaced controlled <input type='number'> with NumericTextInput (type='text' + inputMode='decimal') backed by an internal text buffer. On focus the value is selected; first keystroke replaces 0 cleanly across all browsers. Also accepts optional value/placeholder so the target-headcount field can show empty + a 'current headcount' placeholder. | commits 5 + 6 / ScenarioControls.tsx

## Summary
Spec source | 150526_Manpower Optimization Tool Enhancements.xlsx
PR | https://github.com/BahaaKaaki/manpower-optimization/pull/1
Branch | enhancements/spec-150526-desktop-ui
UI surface targeted | Desktop React (manpower-optimization/desktop)
Items total | 25
Done | 18
Deferred | 6
Answered / Info | 1
Upload time (before) | 94.06s on Manpower.xlsx
Upload time (after) | 19.25s on Manpower.xlsx (~4.9× faster)

## Open discussion points
Topic | Where we are | Questions / actions
BU Selection (#4, #17) | Net-new workflow stage. Spec hints 'after homepage, list of companies, click MGIC' but the same line flags the assumption risk: 'they will always run the app on one laptop'. Needs a design pass. | 1. Where does BU Selection sit in the workflow (before upload, after upload, side-panel)? 2. Is the company list driven by data (a config workbook?) or hardcoded? 3. Do we need per-BU data persistence (different workbooks loaded per BU)? 4. Multi-user / multi-machine collaboration implications.
Hi-res CPC logo (#1) | Current cpc-logo.png is a placeholder. Layout slots are ready; just need the asset. | Saad: please drop the hi-res PNG (transparent background, ~512×512 minimum) into desktop/public/cpc-logo.png and we'll ship it in the next PR.
Dynamic outsourceability per family (#20) | Currently OUTSOURCEABILITY_RULES is hardcoded across 40 job families in manpower_app/rules.py. Making this dynamic affects rules → costs → optimization constraints. | 1. Source: workbook column, in-app editor, or both? 2. Per-BU overrides (ties into #4)? 3. Validation: how to prevent inconsistent states (Fully Outsourceable + a non-zero ratio override)?
Editable ratio drivers (#22) | ratios.py:calculate_driver_values hardcodes the driver profession set per ratio family (e.g. Quarries Foreman → Labor, Skilled Labor, Technician). | 1. UI: free-text label vs structured (activity + profession) picker? 2. Backend: new settings field driver_overrides — needs propagation through calculate_driver_values, the API, and the LP. 3. Should this share data with the partial-config 'driver-based' option in the custom-family wizard?
Target plan driver inputs (#23) | Requires #22 first. Once driver is editable, the target plan needs an input field for the driver headcount so ratios can be recalculated from the user's target. | Open until #22 lands.
Streamlit parity | All changes in this PR target the Desktop React UI. Streamlit (manpower_app/ui_streamlit.py) was deliberately left out of scope. | 1. Is Streamlit still a supported delivery surface, or is it being sunsetted in favor of the Tauri desktop / web container? 2. If kept: do we mirror these UI changes (significant effort) or only the backend changes?
Repo IP / legal | Code currently lives at github.com/BahaaKaaki/manpower-optimization, public. README points to pwc-me-adv-strategyand/manpower-optimization as the canonical source. The Manpower.xlsx in the repo contains employee-level data. | Confirm with PwC IP / legal that public mirroring of this code + the sample workbook is authorized. If not, switch the repo back to private and rotate any historical exposure.
Further upload speed wins (#18 follow-up) | The 94s → 19s win is from caching only. Remaining cost breakdown (cProfile): ~14s pandas .apply(axis=1) row iteration across 14 separate passes, ~6s openpyxl reading the .xlsx. | Two follow-up options: 1. Vectorize the cost calculations (replace row-wise apply with column-wise pandas ops). Bigger refactor, ~5-10× more savings on the apply path. 2. Switch the Excel reader engine to calamine (python-calamine). One-line change in pipeline.py, ~3-5× speedup on the read path, adds one dependency.